## READ ME
BENI Airport DRC: information needed to set up the system
How to use this workbook
1. Fill only the yellow cells. The blue row on each sheet is an EXAMPLE of the format: delete it or overwrite it.
2. Leave a cell blank if you do not know the answer. Never guess a date, number or clause. A blank is safe; a guess is not.
3. Copy values from the executed contract, Particular Conditions and Contract Data, and write the clause or page where each came from.
4. Send the completed file back. Nothing is entered into the live system until a Project Manager or Contract Manager reviews it.
Sheets
1 Contract: particulars, parties, key dates, Time for Completion, price
2 Deadline rules: the 23 notice and deadline matters; period, clause and trigger for each (every rule starts "Not Configured" until approved)
3 Employers Requirements: the requirements the Contractor must meet, word for word
4 KPI targets: your target for each quality measure (blank = no target, no pass/fail shown)
5 Team: every person who will use the system, with official email and phone
6 Report recipients: who receives the issued monthly report
Privacy: phone numbers are held only with the person's WhatsApp consent. Do not put passwords or bank details in this file.

## 1 Contract
1. Contract particulars
Copy from the executed Contract Agreement and Contract Data. Write the clause or page in the last column.
Item | Value | Where in the contract (clause / page)
EXAMPLE: Time for Completion (calendar days) | 000 (replace with the contract figure) | Clause x.x / Contract Data p.x
Contract form and edition (as executed)
Employer
Engineer
Contractor
Commencement Date (dd-mmm-yyyy)
Time for Completion (calendar days)
Accepted Contract Amount
Currency
Performance Security: amount and expiry date
Advance Payment: amount
Defects Notification Period (days)
Delay damages (rate and cap)
Payment period for IPCs (days)
Governing law
Contract language
Time zone for deadlines (default Africa/Lubumbashi)
Particular Conditions: anything that changes timing or notice rules

## 2 Deadline rules
2. Notice and deadline rules
One row per matter. Period and clause must come from the executed contract. Leave blank anything you are unsure of: the system will then show "needs review" and will not calculate a date.
Rule code | Matter | Clause | Trigger event (what starts the clock) | Period (calendar days) | Counting (exclude / include trigger day) | Applies to (Contractor / Employer / Engineer) | Delivery requirement (how it must be sent) | Exceptions | Continuing events treatment | Particular Condition changes? | Source document and page
EXAMPLE | Matter name | 20.2.1 | Date Contractor became aware of the event | 0 | exclude | Contractor | Written notice to the Engineer |  |  |  | Executed contract, p.xx
R-001 | Contractor's Notice of Claim
R-002 | Employer's Notice of Claim
R-003 | Engineer's acknowledgment of a Notice of Claim
R-004 | Detailed Particulars of Claim
R-005 | Responses to claims
R-006 | Interim and final particulars for continuing claims
R-007 | Engineer's determination
R-008 | Notice of Dissatisfaction
R-009 | DAAB referral
R-010 | DAAB decision
R-011 | Amicable settlement period
R-012 | Contractor's programme submission and updates
R-013 | Engineer's response to programme submissions
R-014 | Design submission and review periods
R-015 | Requests for information
R-016 | Variation quotations
R-017 | Payment applications
R-018 | Interim Payment Certificates
R-019 | Payment deadlines
R-020 | Tests on Completion
R-021 | Taking-Over procedures
R-022 | Defects Notification Period obligations
R-023 | Final Statement and Final Payment Certificate

## 3 Employers Requirements
3. Employer's Requirements
One row per requirement. Copy the wording exactly as in the Employer's Requirements. Choose from the drop-downs where offered. Verification methods: separate with commas.
ER section / clause | Title (short) | Requirement text (word for word) | Discipline | Category | Mandatory? (shall = Yes, should = No) | Priority | Applicable standard | Acceptance criteria (how it is proved) | Verification methods
ER 4.2.1 | Terminal roof wind load | The roof shall resist … (copy exact text) | structural | design | Yes | critical | Standard and clause | Test report / calculation accepted by the Engineer | design_review, certificate

## 4 KPI targets
4. Quality KPI targets
Enter the target you want for each measure. Direction is fixed: "higher is better" means a result at or above target passes; "lower is better" means at or below. Leave blank for no target.
Code | Measure | What it counts | Unit | Direction | Your target | Warning level (optional) | Who set this target
Q01 | Employer's Requirements compliance | Share of active requirements verified as compliant (waived ones excluded) | % | higher is better
Q02 | Requirements verified | Share of active requirements with any compliance result recorded | % | higher is better
Q03 | Critical requirements compliance | Compliance of requirements marked critical | % | higher is better
Q04 | Non-compliant requirements | Requirements currently non-compliant or only partly compliant | count | lower is better
Q05 | Inspection first-time pass rate | First inspections accepted (with or without comments) | % | higher is better
Q06 | Inspection rejection rate | All inspections rejected in the period | % | lower is better
Q07 | Inspection turnaround | Average days from request to inspection | days | lower is better
Q08 | Open NCRs | Non-conformance reports not yet closed | count | lower is better
Q09 | Overdue NCRs | Open reports past their due date | count | lower is better
Q10 | Critical NCRs open | Open reports with critical severity | count | lower is better
Q11 | NCR closure time | Average days from identification to closure | days | lower is better
Q12 | Repeat non-conformances | Reports in the period that repeat an earlier one | % | lower is better
Q13 | Test pass rate | Tests passed first time or on retest, as a share of all results | % | higher is better
Q14 | Material first-time approval | Material submissions approved without resubmission | % | higher is better
Q15 | Overdue corrective actions | Actions not verified and past their due date | count | lower is better
Q16 | Audit completion | Planned quality audits actually performed | % | higher is better

## 5 Team
5. Team directory
Official work email and phone with country code (+243… / +254…). WhatsApp consent: Yes only if the person agreed to receive project alerts on that number.
Full name | Role on the project | Organisation | Official email | Phone (+country code) | WhatsApp alerts agreed? (Yes/No) | System access level
Example Person | Resident Engineer | Consultant | name@company.com | +243000000000 | Yes | site_engineer

## 6 Report recipients
6. Monthly report recipients
People and organisations who receive the issued monthly progress report by email. The report is sent only after it has been signed and issued.
Name | Organisation | Email | Role
Example Person | Employer | name@employer.com | Employer's Representative